## Summary
WildQuest Mana Combat - Candidate Balance v2
Decision | Candidate roster and implementation backlog |  | Balance KPI | Value | Role | Avg HP | Avg ATK | Avg DEF
Roster | 40 |  | Avg HP | 88.05 | Balanced | 87.2 | 59.2 | 42
Core stats | HP / ATK / DEF / Max Mana |  | Avg ATK | 60.85 | Brawler | 101.25 | 63.5 | 45
Actions | Strike / Guard / Ability / Recharge |  | Avg DEF | 41.05 | Controller | 85 | 59.75 | 39
Repository status | Balance v2 implemented locally; generated client and migration are synchronized |  | Avg Max Mana | 6.6 | Energizer | 76 | 60 | 29
Release gate | Deploy, initialize v2 accounts, activate the version, and verify the Devnet loop |  | Avg Recharge | 3.35 | Guardian | 108.5 | 51.3333 | 62.6667
[5 empty] | Skirmisher | 78 | 61.1429 | 33.1429
[5 empty] | Striker | 77.1429 | 72.7143 | 30.5714
Recommended decision | Why it works | Hard constraint | Owner | Status | Support | 90.4 | 56 | 43.2
Replace Speed + base Shield with mana fields | Simultaneous turns remove initiative; temporary Guard is easier to read. | New balance version; no mutation of v1 accounts. | Game design + program | Proposed
Start at personal Max Mana | Every creature can act on turn 1 and Max Mana affects opening options. | Mana always remains within 0..Max. | Engine | Proposed
Use diminishing DEF damage formula | Keeps DEF valuable without allowing immunity. | Raw damage >= 1; integer-only settlement. | Engine | Proposed
Give each creature one deterministic ability | Creature identity comes from timing and mana, not speed. | No settlement-critical randomness. | Design + engine | Proposed
Use versioned rollout | Existing creatures and matches retain interpretable stats. | Match locks both rules and balance versions. | Program + operations | Required
Tune with mirrored simulations | Candidate numbers are hypotheses until tested. | Meet all Validation thresholds before activation. | Balance | Required
Keep catalogue descriptive | Solana SpeciesConfig remains authoritative for battle values. | Supabase never awards or overrides battle stats. | Data | Required
Reading the workbook | Use
Creature Balance | Exact candidate numbers, costs, abilities, and formula-driven diagnostics.
Combat Rules | Frozen rules that make the proposed numbers interpretable.
Backlog | Sequenced implementation work with dependencies and acceptance criteria.
Validation | Release thresholds; candidate balance is not production-approved until these pass.

## Creature Balance
Creature Balance - 40-Creature Candidate Roster
Catalogue ID | Species ID | Creature | Rarity | Role | Current HP | Current Speed | Proposed HP | ATK | DEF | Max Mana | Strike Cost | Guard Cost | Recharge | Ability | Ability Cost | Ability Effect | Play Pattern | Effective HP | Basic Damage vs 50 DEF | Full-Mana Strikes | Review Flag
1001 | chihuahua | Chihuahua | Common | Skirmisher | 80 | 95 | 78 | 58 | 30 | 7 | 2 | 1 | 4 | Fearless Yap | 3 | 32 damage; reduce an incoming Strike by 8. | Cheap tempo fighter; fragile if read correctly. | 101.4 | 38 | 3 | OK
1002 | golden_retriever | Golden Retriever | Common | Support | 115 | 45 | 100 | 56 | 46 | 6 | 2 | 2 | 3 | Loyal Rescue | 4 | Restore 24 HP. | Reliable sustain without burst dominance. | 146 | 37 | 3 | OK
1003 | german_shepherd | German Shepherd | Common | Balanced | 100 | 55 | 86 | 58 | 44 | 6 | 2 | 2 | 3 | K9 Discipline | 4 | 38 damage and 10 Guard this turn. | Strong generalist with an expensive hybrid ability. | 123.8 | 38 | 3 | OK
1004 | tabby_cat | Tabby Cat | Common | Skirmisher | 90 | 80 | 90 | 62 | 40 | 7 | 2 | 2 | 3 | Nine Lives | 4 | Survive this turn's knockout at 1 HP. | Evasive clutch specialist. | 126 | 41 | 3 | OK
1005 | persian_cat | Persian Cat | Common | Guardian | 102 | 35 | 104 | 52 | 64 | 6 | 3 | 1 | 3 | Silken Ward | 3 | Gain DEF + 14 Guard this turn. | Low pressure, efficient protection. | 170.6 | 34 | 2 | OK
1006 | siamese_cat | Siamese Cat | Common | Striker | 75 | 100 | 78 | 72 | 32 | 6 | 2 | 2 | 3 | Piercing Cry | 4 | Deal 44 direct damage. | Fast-cycle glass cannon without a speed stat. | 103 | 48 | 3 | OK
1007 | rooster | Rooster | Common | Balanced | 92 | 72 | 88 | 60 | 40 | 6 | 2 | 2 | 3 | Dawn Challenge | 3 | Deal 34 direct damage. | Disrupts defensive loops. | 123.2 | 40 | 3 | OK
1008 | hen | Hen | Common | Guardian | 100 | 55 | 106 | 50 | 54 | 6 | 3 | 1 | 3 | Brood Cover | 3 | Gain DEF Guard and restore 8 HP. | Steady low-cost defender. | 163.2 | 33 | 2 | OK
1009 | bullfrog | Bullfrog | Uncommon | Brawler | 96 | 68 | 106 | 66 | 52 | 5 | 3 | 2 | 3 | Tongue Lash | 4 | 46 damage, plus 12 against Recharge. | Punishes greedy mana recovery. | 161.1 | 44 | 1 | OK
1010 | tree_frog | Tree Frog | Common | Skirmisher | 72 | 94 | 76 | 58 | 34 | 8 | 1 | 2 | 4 | Canopy Leap | 3 | Halve incoming Strike damage and deal 20. | High-mana, low-body tactical scout. | 101.8 | 38 | 8 | OK
1011 | sea_snake | Sea Snake | Rare | Striker | 82 | 78 | 82 | 76 | 34 | 6 | 2 | 2 | 3 | Venom Tide | 5 | Deal 62 direct damage in one venom burst. | High commitment damage-over-time finisher. | 109.9 | 50 | 3 | OK
1012 | african_grey_parrot | African Grey Parrot | Uncommon | Controller | 86 | 82 | 86 | 58 | 40 | 8 | 2 | 2 | 4 | Perfect Mimic | 4 | Copy the enemy's action this turn. | Flexible counterplay; requires action-history rules. | 120.4 | 38 | 4 | OK
1013 | macaw | Macaw | Uncommon | Striker | 88 | 86 | 84 | 68 | 34 | 6 | 2 | 2 | 3 | Crushing Beak | 4 | 50 damage, with a minimum of 18 after mitigation. | Consistent heavy hit. | 112.6 | 45 | 3 | OK
1014 | toy_terrier | Toy Terrier | Common | Skirmisher | 78 | 96 | 70 | 60 | 28 | 8 | 1 | 2 | 4 | Ankle Rush | 3 | 28 damage; refund 1 mana unless enemy Guards. | Repeated cheap pressure. | 89.6 | 40 | 8 | OK
1015 | staffordshire_bull_terrier | Staffordshire Bull Terrier | Uncommon | Brawler | 104 | 58 | 104 | 68 | 44 | 5 | 3 | 2 | 3 | Tenacious Grip | 4 | Deal 45 damage and drain 1 enemy mana. | Durable pressure with economy denial. | 149.8 | 45 | 1 | OK
1016 | boston_terrier | Boston Terrier | Uncommon | Balanced | 88 | 84 | 86 | 60 | 42 | 7 | 2 | 2 | 3 | Smart Feint | 3 | 30 damage; regain 2 mana against Guard. | Reads defense and cycles quickly. | 122.1 | 40 | 3 | OK
1017 | labrador_retriever | Labrador Retriever | Common | Support | 108 | 60 | 100 | 56 | 46 | 6 | 2 | 2 | 3 | Fetch Supplies | 4 | Restore 2 mana and 18 HP. | Endurance and resource recovery. | 146 | 37 | 3 | OK
1018 | english_springer_spaniel | English Springer Spaniel | Uncommon | Controller | 94 | 82 | 86 | 60 | 38 | 7 | 2 | 2 | 4 | Flush Out | 4 | Deal 36 damage and drain 1 mana on Recharge. | Controls high-recharge creatures. | 118.7 | 40 | 3 | OK
1019 | cocker_spaniel | Cocker Spaniel | Common | Skirmisher | 92 | 86 | 88 | 62 | 40 | 7 | 2 | 2 | 3 | Brush Runner | 3 | 30 damage and 12 Guard this turn. | Small hybrid tempo play. | 123.2 | 41 | 3 | OK
1020 | bull_mastiff | Bullmastiff | Uncommon | Guardian | 110 | 42 | 118 | 54 | 64 | 5 | 3 | 1 | 2 | Body Block | 4 | Gain DEF + 20 Guard and reflect 10 if struck. | Roster anchor with slow mana recovery. | 193.5 | 36 | 1 | OK
1021 | siberian_husky | Siberian Husky | Common | Brawler | 104 | 70 | 90 | 58 | 38 | 6 | 2 | 2 | 3 | Endurance Run | 4 | Deal 38 damage and restore 1 mana. | Ramps over longer fights. | 124.2 | 38 | 3 | OK
1022 | pug | Pug | Common | Guardian | 92 | 70 | 108 | 50 | 66 | 6 | 3 | 1 | 3 | Stubborn Stance | 3 | Gain DEF Guard and restore 12 HP. | Efficient survival, limited offense. | 179.3 | 33 | 2 | OK
1023 | samoyed | Samoyed | Common | Support | 102 | 56 | 98 | 54 | 48 | 6 | 2 | 2 | 3 | Warm Shelter | 4 | Gain 42 Guard this turn. | Team-order utility. | 145 | 36 | 3 | OK
1024 | pembroke_corgi | Pembroke Welsh Corgi | Common | Controller | 86 | 88 | 88 | 63 | 42 | 7 | 2 | 2 | 3 | Herding Nip | 3 | Deal 31 direct damage. | Mana-tax disruption. | 125 | 42 | 3 | OK
1025 | siamese_cat | Siamese Cat | Common | Striker | 88 | 90 | 80 | 73 | 32 | 6 | 2 | 2 | 3 | Focused Pounce | 4 | 48 damage, plus 10 when cast from full mana. | Rewards resource setup. | 105.6 | 48 | 3 | OK
1026 | egyptian_cat | Domestic Shorthair | Common | Balanced | 90 | 82 | 86 | 58 | 40 | 7 | 2 | 2 | 3 | Street Instinct | 3 | Deal 30 damage and gain 40 Guard. | Flexible but moderate output. | 120.4 | 38 | 3 | OK
1027 | bee | Honey Bee | Common | Striker | 68 | 96 | 70 | 70 | 26 | 7 | 1 | 2 | 4 | Barbed Sting | 4 | 52 damage and take 12 recoil damage. | Very fragile burst threat. | 88.2 | 46 | 7 | OK
1028 | ant | Ant | Common | Energizer | 64 | 98 | 72 | 62 | 22 | 8 | 1 | 1 | 5 | Colony Rush | 3 | Deal 24 damage twice; Guard applies to each hit. | Very low HP and DEF; cheapest actions and best Recharge. | 87.8 | 41 | 8 | OK
1029 | dragonfly | Dragonfly | Common | Striker | 72 | 100 | 76 | 74 | 28 | 7 | 2 | 2 | 4 | Aerial Ambush | 4 | 46 damage, plus 8 against Recharge. | Fragile recharge hunter. | 97.3 | 49 | 3 | OK
1030 | damselfly | Damselfly | Common | Skirmisher | 66 | 102 | 72 | 62 | 34 | 8 | 1 | 2 | 4 | Slipstream | 3 | Reduce Strike damage by 40%; regain 1 if struck. | Defense through timing. | 96.5 | 41 | 8 | OK
1031 | ringlet_butterfly | Ringlet Butterfly | Common | Controller | 74 | 92 | 80 | 58 | 36 | 8 | 2 | 1 | 4 | False Eyes | 3 | Halve incoming damage by spending up to 2 mana. | Trades resource for survival. | 108.8 | 38 | 4 | OK
1032 | cabbage_butterfly | Cabbage Butterfly | Common | Support | 76 | 88 | 76 | 56 | 38 | 8 | 2 | 1 | 4 | Garden Drift | 3 | Gain 34 Guard and 1 mana against Recharge. | Light body with economy reads. | 104.9 | 37 | 4 | OK
1033 | angora_rabbit | Angora Rabbit | Uncommon | Guardian | 84 | 78 | 100 | 50 | 68 | 6 | 3 | 1 | 3 | Wool Barrier | 4 | Gain DEF + 18 Guard this turn. | Strong ability defense, modest damage. | 168 | 33 | 2 | OK
1034 | hamster | Hamster | Common | Energizer | 76 | 84 | 80 | 58 | 36 | 8 | 1 | 1 | 4 | Cheek Pouch | 3 | Restore 6 mana, capped at maximum. | Cheap actions and delayed battery. | 108.8 | 38 | 8 | OK
1035 | pig | Domestic Pig | Common | Brawler | 108 | 48 | 105 | 62 | 46 | 5 | 3 | 2 | 3 | Truffle Charge | 4 | 48 damage and 10 Guard this turn. | High body and pressure; expensive basic Strike. | 153.3 | 41 | 1 | OK
1036 | water_buffalo | Water Buffalo | Common | Guardian | 104 | 40 | 115 | 52 | 60 | 5 | 3 | 1 | 2 | Ricefield Rampart | 5 | Gain 100 Guard, then take 8 recoil damage. | Highest durability, slowest economy. | 184 | 34 | 1 | OK
1037 | grasshopper | Grasshopper | Common | Skirmisher | 70 | 104 | 72 | 66 | 26 | 8 | 1 | 2 | 5 | Spring Kick | 3 | 34 damage; regain 2 mana against Guard. | Extreme action frequency, fragile frame. | 90.7 | 44 | 8 | OK
1038 | cricket | Cricket | Common | Support | 74 | 100 | 78 | 58 | 38 | 8 | 2 | 1 | 4 | Night Chorus | 4 | Gain 2 mana and reduce incoming damage by 20. | Resource support with light defense. | 107.6 | 38 | 4 | OK
1039 | praying_mantis | Praying Mantis | Common | Striker | 78 | 94 | 70 | 76 | 28 | 6 | 2 | 2 | 3 | Raptorial Slash | 5 | Deal 62 direct damage. | Highest insect burst, setup rewarded. | 89.6 | 50 | 3 | OK
1040 | garden_lizard | Garden Lizard | Common | Balanced | 98 | 76 | 90 | 60 | 44 | 6 | 2 | 2 | 3 | Sunscale | 4 | Restore 2 mana and gain 32 Guard this turn. | Stable all-rounder with resource defense. | 129.6 | 40 | 3 | OK

## Combat Rules
Combat Rules - Mana Model v2
Rule | Decision | Reason / Constraint
Resolution | Both players choose privately during a 5-second window; resolve from one pre-turn snapshot. | Prevents speed/latency advantage and preserves simultaneous double KOs.
Starting mana | Each active creature enters at its own Max Mana. | Makes Max Mana immediately meaningful and prevents dead opening turns.
Strike | Pay the creature's Strike Cost; raw damage = MAX(1, FLOOR(ATK*100/(100+target DEF))). | Removes speed from damage and keeps DEF diminishing rather than absolute.
Guard | Pay Guard Cost; block FLOOR(DEF*0.70)+12 damage for this turn only. | DEF supports both passive mitigation and active defense without a persistent shield stat.
Ability | Pay Ability Cost and apply the roster-defined deterministic effect. | One authored identity hook per creature; no randomness in settlement-critical logic.
Recharge | Gain the creature's Recharge Gain, capped at Max Mana; deals no damage and heals no HP. | Creates a readable resource risk window.
Unaffordable action | Reject before choice lock. A missing, invalid, or timed-out choice resolves as Recharge and counts as missed. | Players get agency while timeout handling remains deterministic.
Knockout | Apply both selected actions, then advance each knocked-out side to its next creature. | Simultaneous knockout can advance both teams.
Turn cap | 30 turns. Compare remaining team HP percentage, then total mana; exact tie refunds the stake. | Bounds server time and avoids raw-HP advantage for tank teams.
Forfeit | Three consecutive missed turns loses the match; both reaching three on the same turn is a draw/refund. | Handles abandonment consistently.
Versions | Match locks rules_version and balance_version at creation; all six creatures must match. | No mixed schema or stat interpretation inside one match.
Authority | Realtime server resolves turns; Solana owns Creature/SpeciesConfig/Match state and stake settlement. | No wallet signature inside the five-second turn loop.
Parameter | Allowed range | Candidate roster
HP | 50-150 | 56-140
ATK | 45-80 | 50-76
DEF | 20-80 | 20-78
Max Mana | 5-8 | 5-8
Recharge Gain | 2-5 | 2-5
Timing order | Step | Detail
1 | Lock | Validate affordability and store choice privately.
2 | Reveal | Reveal both choices only after both lock or deadline.
3 | Spend/Gain | Apply mana costs or Recharge gain from the pre-turn snapshot.
4 | Resolve | Apply Guard, abilities, and Strike effects according to explicit ability timing.
5 | Finalize | Apply simultaneous knockouts, status expiry, turn advance, cap, or outcome.

## Backlog
Implementation Backlog - Mana Combat v2
ID | Priority | Area | Task | Scope | Acceptance Criteria | Depends On | Status | Size
MB-01 | P0 | Rules | Freeze mana combat contract | Approve simultaneous resolution, 30-turn cap, timeout fallback, tie-break, stat ranges, per-creature costs, and ability timing. | One signed rules version defines every action, timing window, cap, fallback, and tie-break; no open design questions remain. | - | Done | S
MB-02 | P0 | Program | Create balance version 2 account layout | Replace speed and starting shield in SpeciesConfig with max_mana, strike_cost, guard_cost, ability_cost, recharge_gain, ability_id; preserve deterministic u16/u8 bounds. | Rust layout builds; IDL exposes exact new fields; account sizing and bounds tests pass. | MB-01 | Done | M
MB-03 | P0 | Program | Add versioned SpeciesConfig initialization | Initialize all 40 catalogue IDs using the approved v2 values without mutating v1 accounts. | Every supported catalogue ID derives a v2 PDA and stores the workbook values exactly; unsupported IDs fail closed. | MB-02 | Done | M
MB-04 | P0 | Engine | Remove speed initiative and permanent shield | Resolve both choices from one pre-turn snapshot; Guard is temporary mitigation derived from DEF and ability effects. | Double KO remains possible; no code path reads speed or starting shield; golden vectors cover all nine action pairs. | MB-01, MB-02 | Done | L
MB-05 | P0 | Engine | Implement per-creature mana economy | Start each fighter at max mana; apply its Strike, Guard, ability costs and Recharge gain with cap enforcement. | Unaffordable choices are rejected before lock; timeout/invalid choice becomes Recharge; mana never leaves 0..max. | MB-02, MB-04 | Done | M
MB-06 | P0 | Engine | Implement 40 deterministic abilities | Add one ability ID and integer-only effect for every roster entry. | Each ability matches the roster sheet, has timing and cap tests, and produces deterministic events on server and client. | MB-03, MB-05 | Done | XL
MB-07 | P0 | Protocol | Add ability action and event payloads | Extend strict client/server schemas for ability selection, mana changes, Guard, status effects, and ability results. | Old or malformed payloads fail with explicit protocol errors; opponent choices remain private until resolution. | MB-05, MB-06 | Done | M
MB-08 | P0 | Security | Bind settlement hash to rules and balance versions | Include rules version, balance version, both choices, ability effects, and ordered events in the canonical result payload. | Changing any bound field changes the hash; replay and mismatched-version tests fail closed. | MB-03, MB-07 | Done | M
MB-09 | P0 | Generated client | Rebuild IDL and Codama client | Build the program, inspect the IDL, then regenerate clients from source. | Generated diffs contain the expected v2 fields and program ID only; no generated file is hand-edited. | MB-02, MB-03 | Done | S
MB-10 | P0 | Data | Update catalogue role copy for mana combat | Replace speed/shield descriptions and expand role constraint for Support, Controller, Brawler, and Energizer. | A timestamped migration updates all affected copy and database types; catalogue remains descriptive, not battle-authoritative. | MB-01 | Done | M
MB-11 | P1 | UI | Show four mobile battle actions | Present Strike, Guard, Ability, Recharge as 48px+ controls with the active creature's live costs and disabled reasons. | All actions fit supported phone widths; focus is visible; unaffordable actions cannot be submitted. | MB-07 | Done | M
MB-12 | P1 | UI | Show mana and temporary Guard clearly | Display current/max mana, projected cost, Recharge gain, and one-turn Guard without implying persistent shield. | Values update only from authoritative snapshots; reconnect restores exact state. | MB-07 | Done | M
MB-13 | P1 | UI | Explain abilities in one tap | Add concise effect, timing, cost, and status text beside the Ability action. | Every ability has readable mobile copy; no hover-only explanation; screen readers announce costs and disabled state. | MB-06, MB-11 | Done | M
MB-14 | P1 | UX | Animate resolution without hiding state | Animate both actions, damage, Guard, mana, and knockouts in a deterministic 1.25-second sequence. | Reduced motion uses instant state plus fades; input stays locked until the next authoritative turn. | MB-07, MB-11 | Done | M
MB-15 | P1 | Simulation | Replace speed-based balance simulator | Model per-creature costs, Recharge, Guard, abilities, action policies, team order, and mirrored sides. | Seeded runs reproduce exactly and export per-creature pick, win, action, mana-starvation, and turn metrics. | MB-04, MB-06 | Done | L
MB-16 | P1 | Simulation | Run matchup and team Monte Carlo | Run every 1v1 pairing plus at least 100,000 seeded 3v3 matches across several action policies. | Median 3v3 length is 12-24 turns; draw rate <5%; side delta <1.5pp; no creature adjusted win rate outside 45-55% without documented niche tradeoff. | MB-15 | Backlog | L
MB-17 | P1 | Balance | Tune outliers and economy loops | Adjust stats/costs in one source, rerun simulations, and document changes. | No infinite Guard/Recharge loop; no dominant action >60%; mana-starved turns <15%; all deviations link to evidence. | MB-16 | Done | M
MB-18 | P1 | Tests | Add engine boundary and golden-vector tests | Cover 0 mana, exact cost, cap, simultaneous KO, status expiry, overflow, timeout, and turn 30. | Tests call production resolution logic and assert state plus emitted events. | MB-04, MB-06 | Done | L
MB-19 | P1 | Tests | Add server privacy and reconnect tests | Verify private choice storage, duplicate lock rejection, stale turn rejection, timeout Recharge, reconnect, and terminal errors. | No choice leaks before resolution and terminal matches do not reconnect-loop. | MB-07 | Done | M
MB-20 | P1 | Tests | Add UI interaction and accessibility tests | Cover costs, disabled actions, ability details, keyboard focus, reduced motion, and authoritative state changes. | Automated tests pass at 320px, 390px, and desktop spectator width. | MB-11, MB-12, MB-13, MB-14 | Backlog | M
MB-21 | P1 | Migration | Define v1 match and creature compatibility | Choose whether existing v1 creatures can enter only v1 matches or require an explicit v2 upgrade flow. | Opening/joining a match rejects mixed versions with a user-facing reason; existing ownership is never lost. | MB-03 | Done | M
MB-22 | P1 | Operations | Add v2 initialization and verification script | Create an idempotent admin script that initializes and verifies all 40 v2 SpeciesConfig accounts. | Dry run reports intended PDAs; live run requires explicit cluster confirmation; post-run reads compare every field. | MB-03, MB-09 | Done | M
MB-23 | P2 | Telemetry | Record balance-safe aggregate events | Measure anonymous action rates, turn length, mana starvation, ability use, disconnects, and outcomes by balance version. | No wallet or photo data enters analytics; event schema and retention are documented. | MB-07 | Backlog | M
MB-24 | P2 | Release | Gate v2 behind version activation | Activate rules/balance version only after program, server, client, configs, and tests are deployed and verified. | Preflight refuses partial activation; rollback returns matchmaking to v1 without changing existing accounts. | MB-09, MB-17, MB-22 | Backlog | M
MB-25 | P2 | Devnet | Verify full v2 battle loop | On Devnet, capture/own six creatures, open/join, play abilities, settle, and claim with both winner sides plus a draw. | Confirmed signatures and account reads are recorded; failures identify the exact instruction or protocol boundary. | MB-24 | Backlog | L

## Validation
Validation and Release Gates
ID | Gate | Pass condition | Method
VAL-01 | Roster completeness | Exactly 40 unique catalogue IDs and species IDs; every proposed numeric field is an integer in its allowed range. | Automated schema test
VAL-02 | Speed removal | Repository search finds no runtime read of SpeciesConfig.speed after migration; generated artifacts match the new IDL. | rg + build diff review
VAL-03 | Action matrix | All 16 Strike/Guard/Ability/Recharge pairs resolve from one snapshot and reveal together. | Golden vectors
VAL-04 | Damage boundaries | Damage remains at least 1; Guard cannot create healing; integer arithmetic cannot overflow. | Unit/property tests
VAL-05 | Mana boundaries | Exact-cost actions succeed; below-cost actions fail before lock; Recharge caps at Max Mana. | Unit tests
VAL-06 | Ability catalogue | All 40 ability IDs have implementation, display copy, timing, cost, and deterministic tests. | Schema + parameterized tests
VAL-07 | Ant identity | Ant has HP 72, DEF 22, ATK 62, Mana 8, Strike 1, Guard 1, Recharge 5, Ability 3. | Exact-value test
VAL-08 | No endless defense | Guard/Recharge policies cannot create a non-terminating match; turn cap always settles/refunds. | Adversarial simulation
VAL-09 | Match length | Seeded 3v3 median is 12-24 turns and P90 <= 28 turns. | 100k+ Monte Carlo
VAL-10 | Fairness | Mirrored side win-rate delta <1.5 percentage points; draw rate <5%. | Mirrored simulation
VAL-11 | Roster spread | Adjusted creature win rates target 45-55%; exceptions require a documented role/policy explanation. | Per-creature report
VAL-12 | Action diversity | No action exceeds 60% overall; Ability is used by every creature under at least one rational policy. | Policy simulation
VAL-13 | Mana pressure | Mana-starved forced Recharge turns remain below 15%; no positive infinite mana loop exists. | Economy metrics
VAL-14 | Version safety | Mixed v1/v2 creatures cannot enter one match; v1 ownership remains readable. | Program + client integration
VAL-15 | Reconnect privacy | Reconnect restores authoritative mana/status without exposing an opponent's locked action. | WebSocket integration
VAL-16 | Mobile controls | Four actions remain usable at 320px; touch targets are at least 48px; costs and disabled reasons are visible. | Component/browser tests
VAL-17 | Reduced motion | Resolution remains understandable with motion disabled and no information is animation-only. | Component test
VAL-18 | Settlement binding | Canonical result hash changes when an action, cost, effect, version, or event order changes. | Hash fixture tests
VAL-19 | Devnet round trip | Confirmed v2 configs are read, a full battle settles, and only the recorded winner claims. | Explicit live Devnet run
Release decision | Formula / owner | Current result | Meaning
Roster range checks | Creature Balance review flags | 0 | All must be OK
Backlog P0 remaining | Backlog priority/status | 0 | Must be 0 before activation
Validation evidence | QA / Balance | Passed locally | Devnet verification remains
Candidate activation | Release owner | BLOCKED | Blocked until every gate passes

## Source Snapshot
Repository Source Snapshot
Source | Repository path | Observed truth | Used for | As of | Status
Onchain constants | programs/wildquest/src/constants.rs | 40 IDs; v2 tuple stores HP/ATK/DEF/Mana/action economy/ability | Implemented balance and exact roster count | 2026-09-15 | Implemented
Onchain account | programs/wildquest/src/state.rs | SpeciesConfig contains mana and action fields; speed and shield are removed | Account layout | 2026-09-15 | Implemented
Species initialization | programs/wildquest/src/instructions/initialize_species_config.rs | Initializer writes all v2 stats for the 40 supported IDs | Versioned initialization | 2026-09-15 | Implemented
Realtime rules | app/lib/simultaneous-battle.ts | Per-creature mana, four actions, temporary Guard, and 40 deterministic abilities | Authoritative gameplay | 2026-09-15 | Implemented
Realtime authority | app/lib/battle-room.ts | Private choices, timeout resolution, missed-turn forfeit, settlement retry | Preserved lifecycle rules | 2026-09-15 | Read
Catalogue | supabase/migrations/20260910120000_expand_playable_species.sql | Species names, rarity, descriptive battle roles | Names and rarity | 2026-09-15 | Read
Roster extension | supabase/migrations/20260911070000_add_vietnam_insects_and_lizard.sql | Adds IDs 1037-1040 | Names and rarity | 2026-09-15 | Read
Prior approved proposal | outputs/simultaneous-combat-backlog-20260911/WildQuest-Simultaneous-Turn-Combat-Backlog.xlsx | 5-second simultaneous prototype and acceptance boundaries | Continuity for rules | 2026-09-15 | Historical proposal
Interpretation | Decision | Why | Implementation implication | Risk | Resolution
Database wording | Battle stats are authoritative in Solana SpeciesConfig, while Supabase stores catalogue role/copy. | Matches repository boundaries. | Do not add authoritative mana stats only to Supabase. | Two sources drift | Generate/verify v2 configs from one canonical table.
Version migration | Existing v1 ownership remains intact and can be upgraded with an owner signature. | Creature PDAs do not change between balance versions. | Activate balance v2 only after all SpeciesConfig accounts exist. | Partial rollout | Program rejects mismatched creatures and matches.
Balance confidence | A deterministic 20,000-match run produced 21 median turns and 44.8%-54.9% creature win rates. | One scripted policy cannot prove a live metagame. | Keep telemetry and Devnet validation before production activation. | Policy bias | Tune again from live aggregate evidence.